RAID Log Enterprise Document Management System — EDMS v1.0 Generic Metrics — Risks, Assumptions, Issues, Dependencies Internal — Restricted · ARB Ref: EARR-2026-0142

| Field | Value |
| --- | --- |
| Document ID | EDMS-GEN-002 |
| Domain | Generic Metrics — Cross-Cutting |
| Solution | Enterprise Document Management System (EDMS) v1.0 |
| Author | Arjun Mehta · Platform SA |
| Version | v1.1 — Current as of 14-Apr-2026 |
| ARB Reference | EARR-2026-0142 |

This RAID Log consolidates all Risks, Assumptions, Issues, and Dependencies across all architecture domains for EDMS v1.0. Items are rated by Impact (HIGH/MEDIUM/LOW) and tracked with owners and status. This is a living document updated continuously through the ARB process.

# 1. RISKS

Active Risks — Architecture & Design

| ID | Domain | Risk Description | Likelihood | Impact | Mitigation / Design Response | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-01 | Security | VAPT not yet completed for production environment (platform is pre-production). VAPT is mandatory before go-live under Bank Security Standard v3.1. | HIGH | CRITICAL | VAPT booked with approved vendor (CrowdStrike). Target completion 31-Jul-2026. Security controls designed-in and reviewable now. Blocker on production approval until VAPT results submitted. | Security Team | OPEN — BLOCKER |
| RISK-02 | Infrastructure | EKS 1.29 reaches End-of-Support (EOS) November 2025. Running unsupported EKS version violates Bank Security Standard v3.1 (no unsupported runtimes in production). | HIGH | CRITICAL | Upgrade plan approved. Target: EKS 1.30 by Oct 2025. Infra team change window allocated. No production traffic until upgrade complete. | Infra Lead | IN PROGRESS |
| RISK-03 | Integration | IBM MQ client library v9.3 reaches EOS December 2025. Continued use beyond EOS violates security policy. | HIGH | HIGH | Upgrade to IBM MQ 9.4. 3-day effort. Regression tested in staging. Target: complete Oct 2025 before platform launch. | Integration Arch | IN PROGRESS |
| RISK-04 | Application | Circuit breakers not implemented on RDS and OpenSearch synchronous call paths. A database failure could cascade across all dependent services. | MEDIUM | HIGH | Circuit breaker library (resilience4j / tenacity) selected. Implementation scoped in Sprint 7. Target: before staging cutover. | Dev Lead | OPEN — Action ACT-06 |
| RISK-05 | Application | Golang (used for Audit Service) is not on the bank's approved technology stack. If waiver denied, Audit Service must be rewritten in Python. | MEDIUM | MEDIUM | Golang waiver submitted (ADR-APP-02). Fallback Python design documented. Stack approval committee meets May-2026. Fallback path adds ~4 weeks if required. | EA + Dev Lead | OPEN — Waiver Pending |
| RISK-06 | Data | GDPR right-to-erasure: KYC PII stored in JSONB metadata may persist after document binary is deleted. Metadata tombstoning must null-out PII fields. | HIGH | HIGH | PII fields identified and flagged in metadata schema. Disposal job updated to null-out PII fields before tombstoning. DPO certification required before launch. | Data Arch + Legal | IN PROGRESS |
| RISK-07 | Business | Regulatory scope change — RBI may issue updated data localisation circular affecting storage regions for Indian customer data. | LOW | HIGH | Monitor RBI circulars. S3 bucket region pinning architecture supports rapid reconfiguration. Legal team engaged to track regulatory developments. | Compliance + Legal | MONITORING |
| RISK-08 | Business | LOB adoption risk — 7 LOBs committed at programme level but only 4 have active onboarding plans. TCO model assumes 7 LOBs sharing platform cost. | MEDIUM | MEDIUM | Executive sponsorship confirmed at CTO level. Architecture Forum roadmap commitment logged. Onboarding templates provided to all 7 LOBs. | Platform PM | OPEN |
| RISK-09 | Infrastructure | DR failover has not been tested. RTO of 4 hours and RPO of 1 hour are designed targets, not validated. | MEDIUM | HIGH | DR drill scheduled Q3 2026. DR runbook INFRA-RB-001 authored and reviewed. Must complete before production go-live. | Infra Lead + SRE | OPEN — Scheduled |
| RISK-10 | Integration | MQ message size limit of 10 MB is insufficient for large Trade Finance shipping documents (up to 50 MB). Silent failures possible if not handled. | MEDIUM | HIGH | MQ consumer detects oversize messages and redirects to REST API upload path. Integration guide updated. Tested with 50 MB payload in development. | Integration Arch | RESOLVED |

# 2. ASSUMPTIONS

| ID | Domain | Assumption | Impact if Wrong | Validation Status | Owner |
| --- | --- | --- | --- | --- | --- |
| ASMP-01 | Business | Each LOB will provide a signed Data Classification Register before EDMS onboarding. | HIGH — affects S3 bucket policy, KMS key assignment, and retention policy configuration per LOB. | 5 of 7 submitted. Trade Finance and Risk pending. Tracked as dependency DEPS-03. | LOB SAs |
| ASMP-02 | Business | LOB retention policies are stable and legally signed off before onboarding. No policy changes after initial configuration. | HIGH — policy engine design assumes stable schedules. Mid-lifecycle changes require migration process. | Retention schedules collected from 5 LOBs. Legal sign-off template circulated. 2 LOBs pending. | Legal + LOB SAs |
| ASMP-03 | Integration | All LOBs consuming via REST API will use OAuth2 JWT tokens issued by central IAM (AWS Cognito) by production launch. | HIGH — non-JWT LOBs require additional integration work and increase attack surface. | 4 of 7 LOBs confirmed. 3 LOBs (Legacy Ops, Trade Finance legacy, Compliance) using API keys in transition. Migration plan with June-2026 deadline. | IAM + LOB SAs |
| ASMP-04 | Application | ClamAV virus definitions will be automatically updated daily via container image refresh in production. | HIGH — stale definitions reduce security posture; newly-deployed malware may not be detected. | Image update pipeline configured and tested in dev. Nightly ECR image rebuild confirmed. | DevSecOps |
| ASMP-05 | Infrastructure | AWS ap-southeast-1 (Singapore) has sufficient reserved capacity for auto-scaling to 20 EKS nodes during peak processing. | MEDIUM — capacity constraints could cause scale-out failures during peak load events. | AWS capacity reservation for m6i.2xlarge in ap-southeast-1 requested. Response pending. | Cloud Ops |
| ASMP-06 | Data | OpenSearch CDC pipeline (Debezium from RDS) can maintain < 60 second lag between metadata write and search index update. | MEDIUM — search results may lag metadata updates. Acceptable for document retrieval use case. | Debezium PoC demonstrated 8-second average lag. Production configuration in Sprint 6. | Data Eng |

# 3. ISSUES

| ID | Domain | Issue Description | Impact | Resolution / Action | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| ISSUE-01 | Security | 3 of 12 EDMS service accounts are missing LOB scope in their IAM policies. These service accounts have broader-than-necessary S3 access. | HIGH — principle of least privilege violated; potential for cross-LOB data access by misconfigured service. | IAM policy reviewed. Updated scoped policies authored. Peer review in progress. Target: resolved by 30-May-2026 (Action ACT-02). | IAM Lead | IN PROGRESS |
| ISSUE-02 | Application | Metadata Service and Retention Service unit test coverage below 80% threshold (79% and 76% respectively). | MEDIUM — insufficient test coverage increases risk of regressions in critical lifecycle management code. | Coverage improvement work in Sprint 7. Target: all services ≥ 80% before staging promotion. (Action ACT-10) | Dev Lead | IN PROGRESS |
| ISSUE-03 | Business | Compliance LOB has an overlapping document store managed by external vendor under contract until Q3 2026. Migration timing at risk. | MEDIUM — dual-running cost; potential for data divergence during migration period. | Vendor contract review in progress. Procurement negotiating early exit clause. Target migration: Q3 2026. | Procurement + Compliance SA | IN PROGRESS |
| ISSUE-04 | Integration | Compliance LOB SFTP integration depends on external vendor migrating from FTP to SFTP. Vendor timeline uncertain. | MEDIUM — blocks Compliance LOB go-live on EDMS if vendor delays. | Vendor migration plan received. Target: Apr-2026. Escalation path agreed if delayed. | Compliance SA | IN PROGRESS |
| ISSUE-05 | DevSecOps | SAST (SonarQube) not yet integrated in CI/CD pipeline. SAST results are manual-only at present. | HIGH — security vulnerabilities may not be caught before deployment. Blocks production approval. | SAST integration scoped in Sprint 8. ADR-DSOPS-01 documents the decision. Target: before production. (Action ACT-08) | DevSecOps Lead | IN PROGRESS |
| ISSUE-06 | Security | SIEM (Splunk) authentication anomaly alerting rules for EDMS not yet configured. | MEDIUM — anomalous authentication events (credential stuffing, privilege escalation) may not be detected in real-time. | Splunk rules authored. Review by Security Ops. Target: 15-Jun-2026 (Action ACT-03). | Security Ops | IN PROGRESS |

# 4. DEPENDENCIES

| ID | Domain | Dependency | Dependent On | Impact if Not Met | Target Date | Status |
| --- | --- | --- | --- | --- | --- | --- |
| DEPS-01 | Infrastructure | OpenSearch cluster network peering must be completed before Search Service can be deployed. | Infra Team — ticket INFRA-2026-114 | HIGH — Search Service blocked; full-text document search unavailable. | 30-Mar-2026 | IN PROGRESS |
| DEPS-02 | Business | MAS regulatory reporting automation (Compliance LOB) is blocked until EDMS Metadata API v1 is available. | EDMS Platform Team | HIGH — Compliance LOB go-live blocked without API. | Q2 2026 | ON TRACK |
| DEPS-03 | Business | Trade Finance and Risk LOB onboarding blocked until Data Classification Registers are submitted. | Trade Finance SA + Risk SA | HIGH — S3 bucket policy and KMS key cannot be provisioned without classification. | 30-Apr-2026 | OVERDUE — Follow-up required |
| DEPS-04 | Data | OpenSearch metadata search accuracy depends on Debezium CDC pipeline from RDS being live. | Data Engineering Team | MEDIUM — Search reflects stale data until CDC active. | Sprint 6 (May-2026) | IN PROGRESS |
| DEPS-05 | Integration | JWT migration for 3 legacy LOBs (API key → OAuth2) depends on IAM team provisioning OAuth2 client credentials. | IAM / Identity Platform Team | MEDIUM — API key LOBs remain in transition (higher risk) until migrated. | Jun-2026 | ON TRACK |
| DEPS-06 | Infrastructure | AWS capacity reservation for production auto-scaling (m6i.2xlarge, ap-southeast-1) must be confirmed. | Cloud Operations / AWS Account Team | MEDIUM — Burst scaling may fail during peak processing if capacity not reserved. | 30-Apr-2026 | PENDING RESPONSE |
| DEPS-07 | Security | VAPT must be completed and results submitted before production go-live approval. | Approved VAPT Vendor (CrowdStrike) | CRITICAL — Production launch blocked without VAPT results. | 31-Jul-2026 | BOOKED |

# 5. RAID Summary Dashboard

| Category | Total Items | OPEN / In Progress | Resolved / Monitoring | Blockers |
| --- | --- | --- | --- | --- |
| Risks | 10 | 9 | 1 (RISK-10 Resolved) | 2 (RISK-01 VAPT, RISK-02 EKS EOS) |
| Assumptions | 6 | 2 (ASMP-03, ASMP-05 unconfirmed) | 4 confirmed | None |
| Issues | 6 | 6 In Progress | 0 | 2 (ISSUE-01 IAM, ISSUE-05 SAST) |
| Dependencies | 7 | 5 In Progress / On Track | 0 | 1 (DEPS-07 VAPT) |
| TOTAL | 29 | 22 | 5 | 5 items requiring ARB attention |